## Sheet1
Genral Tasks | Average Days Per Task | 4 |  | Progress | 66.67%
Description | Start Date | End Date | Column1 | Severity | Completed
Environmentalize secret kets for APIs | 2023-02-27 | 2023-03-03 | 4 |  | Done
Finalize distribution procedure of application and authorization of new profiles |  |  | 0 |  | To-Do
Bug Fix: Predict is jumping an index due to weird character in some PDFs | 2023-03-07 | 2023-03-15 | 8 |  | Done
Overnight Script | Average Days Per Task | 4 |  | Progress | 66.67%
Description | Start Date | End Date | Column1 | Severity | Completed
Get invoices from specified email |  |  |  |  | Done
Able to sort by multi page invoices |  |  |  |  | Done
Filter memos | 2023-02-03 | 2023-02-03 |  |  | Done
Get batched pdfs for previous day
Push PDFs to model
Segregate unreadable PDFs (considering allowing the user to do such)
Fail case if script failed or ran into a bug overnight (contact admin - whoever assigned)
Parse returned data from Ap personnel to the finance server. (need test data to have a meeting to flesh out what data goes where)
Machine Learning Model
| Start Date | End Date |  | Severity | Completed
Trained successfully on initial two months of data
Able to be iteratively trained
Set a data collection period and train date
AP Personnel Interface
| Start Date | End Date |  | Severity | Completed
Interface to correct generated data
Push corrected batch back to script
Push corrected data to model’s data bank for training
Create application layout
Notify user if PDF script was successful
Payment Server
Steps
run overnight script
Notes
api keys? | 3
email rules? | 3
admin rights?
bill to field? | 3
description? | 3
Changes made
Pushed predictions to excel file